## Project Plan
ID | Task | Status | LOE Est | Deadline | Actual Start Date | Actual End Date | Notes
1 | Documentation
1.1 | Project Charter | 100% | 1 hr | 2023-06-12 | 2023-06-12 | 2023-06-12
1.2 | Requirements Document | 100% | 2 hrs | 2023-06-12 | 2023-06-12 | 2023-06-12
1.3 | Project Plan | 100% | 1 hr | 2023-06-12 | 2023-06-12 | 2023-06-12
1.4 | Data Schema | 100% | 4 hrs | 2023-06-21 | 2023-07-10 | 2023-07-10 | Updated 2023-07-17
1.6 | Data Use Licenses | 100% | 1 hr | 2023-07-10 | 2023-07-10 | 2023-07-10 | All data acquired from public government web sites
2 | Setup GitHub Project
2.1 | Setup Directories | 100% | 0.5 hr | 2023-06-12 | 2023-07-10 | 2023-07-10
2.2 | Create README Files | 100% | 1 hr | 2023-06-12 | 2023-07-10 | 2023-07-10
0 | Skill Development and Subject Research | [5 empty] | Delete this section when finished…
0.1 | Understanding the Legislative Process |  |  | 2023-06-13 |  |  | Why are there different # of laws passed by chamber?
0.2 | Cheat Sheet for Terms used in the Resume |  |  | 2023-06-13
0.3 | Tableau Refresher |  |  | 2023-06-15
0.4 | Tableau Story Tutorial |  |  | 2023-06-16
0.6 | Research QA / Usability Checklists for Data Projects |  |  | 2023-06-20
3 | Data Collection & Cleanup
3.1 | Data Entry - Resumes of Congressional Activity | 100% | 1 wk | 2023-06-13 | 2023-06-12 | 2023-06-21
3.2 | Data Entry - Partisan Makeup of Congress | 100% | 1 hr | 2023-06-13 | 2023-07-10 | 2023-07-10
3.3 | Data Cleanup and Transformation | 100% | 4 hrs | 2023-06-13 | 2023-06-22 | 2023-07-06
4 | Data Visualizations
4.1 | Worksheets:
4.1.1 | Text Table - Partisan Makeup | 100% | 1 hr | 2023-07-21 | 2023-07-17 | 2023-07-17
4.1.2 | Text Table - Senate Activity | 100% | 1 hr | 2023-07-21 | 2023-07-06 | 2023-07-17
4.1.3 | Text Table - House Activity | 100% | 1 hr | 2023-07-21 | 2023-07-06 | 2023-07-17
4.1.4 | Text Table - Confirmation Activity | 100% | 1 hr | 2023-07-21 | 2023-07-17 | 2023-07-17
4.1.5 | Chart - Working Days |  | 2 hrs | 2023-07-21
4.1.6 | Chart - Partisan Membership |  | 2 hrs | 2023-07-21
4.1.7 | Chart - Laws and Vetoes |  | 2 hrs | 2023-07-21
4.1.8 | Chart - Bills and Measures |  | 2 hrs | 2023-07-21
4.1.9 | Chart - Votes and Quorum Calls |  | 2 hrs | 2023-07-21
4.1.10 | Chart - Nominations |  | 2 hrs | 2023-07-21
4.2 | Dashboard |  | 4 hrs | 2023-07-28
4.3 | Tableau Story |  | 8 hrs | 2023-07-28
4.3 | Publish Packaged Workbook |  | 1 hr | 2023-07-28
5 | Testing / QA
5.1 | Proofread / Review Terminology Used |  | 1 hr | 2023-08-04 |  |  | How to do this?
5.2 | Review Visuals for Ease of Use |  | 4 hrs | 2023-08-04 |  |  | How to do this?
5.3 | Review Deliverables for Adherence to Best Practices |  | 4 hrs | 2023-08-04 |  |  | How to do this?
6 | Project Closeout:
6.1 | Review / Cleanup Documentation:
6.1.1 | Project Charter |  | 1 hr | 2023-08-11
6.1.2 | Project Plan |  | 1 hr | 2023-08-11
6.1.3 | Data Schema |  | 1 hr | 2023-08-11
6.1.4 | Data Use Licenses |  | 1 hr | 2023-08-11
6.2 | GitHub Project Review / Cleanup |  | 1 hr | 2023-08-11